## Sheet1
TrueValue - Order Orchestration Service Integration
S.No | Action | Source | Destination | Trigger point | Activity Description | API Dev Effort (Man days)
1 | Sales order | OOS | WMS | Post order creation in OOS | API Development | 2
2 | Pre-Delivery Cancel | OOS | WMS | In Order allocation, Picker assignment, Picking, Quality (Before delivery confirmation) | API Development - Need to apply Cancellation and Inventory logic in all processes | 10
3 | Inbound Return | OOS | WMS | Post Return order creation in OOS | API Development | 2
4 | Order Status update | WMS | OOS | Push status and Qty details to OOS (received, picked,shipped) | Webhook API - Requires development to Push the details to OOS API | 3
5 | Inventory update | WMS | OOS | Push inventory details at all Inventory updates (Putaway, Picking, stock adjustment ) | Webhook API - Requires development to Push the details to OOS API | 6
[5 empty] | System Testing | 2
[5 empty] | Integration Testing with OOS | 3
[5 empty] | Total Effort (In Man days) | 28
[5 empty] | Cost (USD $) per Man day | 125
[5 empty] | Total Cost in USD ($) | 3500